## 1. Discovery
# | Task/Activity | Responsible Role | Outcome
| The Learning Cycle - Lean Startup | Business Owner
| Safe Lean startup cycle picture |  | The Lean Startup cycle doesn’t produce features—it produces clarity on what to build next. Learning → Decision → Direction
The North Star - Strategic Theme and Vision
6 | Define strategic level business Objectives | Business Owner | it’s aligned direction that drives measurable business impact across the organization.
7 | Establish product vision | Product Manager | A product vision creates shared direction and purpose, enabling teams to build the right product for the right customer outcomes. The vision drives: Vision → Strategy → Roadmap → Backlog.
| Portfolio Backlog - Epics | Product Manager
9 | Classify epics (Functional/Non-Functional) |  | It aligns Strategy to Execution. Portfolio epics convert strategy into prioritized, outcome-driven investments that guide execution at scale. Strategic Alignment + Focused Investment + Measurable Business Value
10 | Write epic summary and description
11 | Define business outcomes
12 | Establish acceptance criteria
13 | Identify leading indicators
14 | Document non-functional requirements
| Customer Centric - Design Thinking | Product Manager
15 | Conduct Gemba/Interviews |  | Design Thinking ensures we solve the right problem with solutions customers truly value. Empathy → Problem Clarity → Validated User-Centric Solution
16 | Create user personas
17 | Build empathy maps
18 | Map customer journey
19 | Define features
20 | Design architecture
21 | Document customer problem
22 | Define business impact
| Setup Portfolio Kanban | Agile Coach
23 | Configure portfolio Kanban board |  | Portfolio Kanban brings transparency and flow to strategic initiatives, enabling better prioritization and faster value delivery. Visibility + Flow + Focus + Better Investment Decisions
24 | Define work item types
25 | Establish WIP limits
| Roadmap and Release Planning | Product Manager | It’s a coordinated, realistic plan that turns strategy into deliverable value. It alignsto strategy and Vision. Aligned Plan + Prioritized Value + Predictable Delivery
26 | Align features across timeline
27 | Calculate WSJF prioritization
29 | Identify risks and dependencies
30 | Create PI/Quarterly roadmap
31 | Define 2-3 year solution roadmap
| Define Minimum Viable Product & Minimum Marketable Product | Product Manager
32 | Define MVP for learning/validation |  | MVP helps us learn fast; MMP ensures we deliver enough value to succeed in the market. Faster Learning + Focused Build + Confident Market Launch
33 | Define MMP for market-ready value
34 | Align product goals with roadmap

## 2. Build and Test
# | Task/Activity | Responsible Role | Outcomes | Toolkit
| Features | Product Manager
1 | Write feature summary |  | A well-defined feature turns an idea into a deliverable unit of value with clear purpose and success criteria. Clear Value + Defined Scope + Execution Readiness
2 | Document feature description
3 | Define benefit hypothesis
4 | Establish feature acceptance criteria
| Story Mapping | Product Owner | Story mapping transforms ideas into a user-centered, prioritized plan for incremental delivery. Shared User Journey + Prioritized Backlog + Clear MVP & Releases
| Story | Product Owner
| Summary |  | A story turns intent into a small, deliverable piece of customer value that can be built, tested, and validated quickly. Small Value Delivered + Tested + Ready for Feedback
Acceptance Criteria
Software Engineering Excellence - Ways of Working
7 | Backlog refinement | Product Owner | Backlog refinement ensures the team always has the right work, clearly defined and ready for development. Clear + Prioritized + Execution-Ready Backlog
8 | Apply UI/UX best practices & Wifeframes | UX Designer | Great UI/UX turns functionality into a seamless experience that users adopt, trust, and rely on. Intuitive Experience + Higher Adoption + Better Business Results
9 | Perform sprint/iteration planning | Scrum Master | Sprint planning ensures the team starts with clarity, focus, and a realistic plan to deliver value. Clear Sprint Goal. Clear Goal + Committed Work + Execution Readiness
10 | Write unit test cases (TDD) | Developer | TDD builds quality into the code from the start, enabling faster, safer, and more reliable delivery. Built-in Quality + Faster Feedback + Confident Delivery
| Creating Story test case | Tester | Story test cases turn requirements into verifiable outcomes, ensuring quality is built and proven at every step. Clear Validation + Better Coverage + Higher Quality
12 | Implement code | Developer | Source Code with functionality ready to deploy.
| Clean coding practices. Devin can support. (Code Cleanup) | Developer | Clean coding practices create software that is easy to change, reliable to run, and sustainable to scale. Readable + Maintainable + Reliable + Scalable Code
| Security coding practices | Developer | The outcome of applying secure coding practices is not just compliance—it’s software that is resilient to attacks, protects data, and maintains user trust from the ground up. Secure Software + Reduced Risk + Faster Mitigation + Customer Trust | For PO/PM: https://pages.git.i.mercedes-benz.com/gcs/KnowledgeBase/devsecops_docs/Handbooks/manager/ For Developer: https://pages.git.i.mercedes-benz.com/gcs/KnowledgeBase/devsecops_docs/Handbooks/sec-developer/
| Sonar lite & Blackduck to take care of Security Vulnarabilities. | Developer | Built-in Quality. Devin can be used.
| Understand branching strategy | Developer | A well-understood branching strategy enables teams to collaborate efficiently while maintaining code stability and delivery speed. Structured Collaboration + Safer Integration + Faster Delivery
13 | Code commit in future branch & Create pull request | Developer | Commits and pull requests ensure code changes are integrated safely, reviewed thoroughly, and continuously improved. Controlled Integration + Quality Assurance + Collaboration
14 | Conduct peer review | Tech Lead | Peer reviews improve quality and spread knowledge, ensuring every change is better before it is merged. Better Quality + Early Defect Detection + Shared Ownership
15 | Commit to version control | Developer | Version control commits create a reliable history of changes, enabling safe collaboration and continuous delivery. Traceability + Safe Progress + Collaboration + Integration Readiness
16 | Execute Automation test cases in CI CD | Automation in CI CD Pipeline | Automated tests in CI/CD ensure every change is validated instantly, enabling fast and reliable delivery. Continuous Quality + Faster Feedback + Safer Releases
| Static Code Analysis |  | Static code analysis ensures quality and security are validated automatically before code is executed. Early Issue Detection + Improved Quality + Enhanced Security
| Code Coverage 85% |  | Code coverage provides confidence that our system is well-tested and safe to change. Visibility + Confidence + Reduced Risk
| Sonar & Blackduck for Security Vulnarabilities run as part of CI CD Pipeline |  | Integrating Sonar and Black Duck into CI/CD ensures every release is automatically checked for quality and security risks before it reaches customers. Continuous Security + Early Detection + Faster Mitigation + Safe Releases
| Close High & Critical reported bugs from sonar & Blackduck before next deployment | Developer | Closing High and Critical Sonar and Black Duck issues ensures our code is secure, clean, and ready for reliable delivery. Secure + Clean + Maintainable + Release-Ready Code
17 | Deploy to Dev environment | CI CD Pipeline | Fast feedback, early validation, and a constantly usable system for development and testing. Fast Feedback + Early Validation + Continuous Integration
| Test Story as per Acceptance criteria with proper test cases | Tester | Verified, high-quality functionality that meets the intended user value. Verified Functionality + High Quality + Release Confidence
| Close all High and Critical defects detected | Developer | Stable, reliable, and release-ready increment that users can trust. Stable + Reliable + Release-Ready Product Increment
| Definition of Done for increment | Developer | it’s a shared, enforceable standard that guarantees every increment is truly complete, usable, and releasable. Releasable Increment + Consistent Quality + Shared Clarity
| Update automation suite for new features | Tester | Keeping the automation suite updated ensures every new feature is protected and validated continuously. Continuous Regression Safety + Faster Feedback + Higher Confidence
| Create Feature level Test Case | Tester | Feature test cases ensure every feature is validated comprehensively, delivering reliable and complete user value. End-to-End Validation + Full Coverage + Release Confidence
| Test Feature based on Benefit Hypothesis and Acceptance Criteria | Product Owner | Testing against benefit hypothesis and acceptance criteria ensures we build features that not only work—but truly deliver value. Functional Validation + Value Validation + Confident Decisions
CI Pipeline Mechanics
18 | Configure version control (GitHub/GitLab) | DevOps Engineer | Configuring version control establishes the foundation for secure, collaborative, and scalable software delivery. Centralized Code + Controlled Collaboration + DevOps Enablement
19 | Setup automated build triggers | DevOps Engineer | Automated build triggers ensure every change is instantly validated, enabling faster and more reliable delivery. Instant Builds + Fast Feedback + Reliable CI/CD Foundation
20 | Configure build tools (Maven/Gradle) | DevOps Engineer | Configuring build tools ensures every build is consistent, automated, and ready for seamless integration into the delivery pipeline. Standardized + Automated + Reliable Build Process
21 | Setup CI tools (Jenkins/GitHub Actions) | DevOps Engineer | CI tools ensure every code change is automatically integrated and validated, enabling faster and more reliable delivery. Automated Integration + Fast Feedback + Reliable Pipeline
22 | Implement unit test execution | DevOps Engineer | Unit test execution ensures every piece of code is validated early, enabling faster, safer, and higher-quality development. Early Bug Detection + Built-in Quality + Safe Development
23 | Configure static code analysis | DevOps Engineer | it’s continuous, automated enforcement of code quality and security before the code ever runs. Early Issue Detection + Improved Quality + Enhanced Security
24 | Setup artifact creation/storage | DevOps Engineer | it’s a controlled, traceable, and reusable way to manage build outputs across the delivery pipeline. Versioned Artifacts + Reliable Deployments + Full Traceability
| Integrate Automated testing Test cases as part of daily build | DevOps Engineer | Integrating automated tests into daily builds ensures continuous validation and keeps the product always ready for release. Daily Quality Assurance + Faster Feedback + Stable Codebase
| Security Vulnarabilities - Blackduck as part of daily build | DevOps Engineer | Daily Black Duck scans ensure security risks are identified and addressed early, preventing vulnerable code from reaching production. Continuous Security + Early Detection + Faster Mitigation + Safe Releases
Security as Non-Functional Requirement
25 | Implement SAST (Static Application Security Testing) | DevOps Engineer | SAST ensures security vulnerabilities are identified early in development, enabling safer and more reliable software delivery. Early Vulnerability Detection + Built-in Security + Faster Mitigation
26 | Configure dependency scanning | DevOps Engineer | Dependency scanning ensures third-party risks are continuously identified and controlled before they impact production. Dependency Visibility + Risk Control + Continuous Security
27 | Setup secrets management | DevOps Engineer | Secrets management ensures sensitive data is securely stored, accessed, and managed—protecting the system from credential-related risks. Secure Secrets + Controlled Access + Reduced Risk
28 | Verify no critical vulnerabilities (CVSS > 7) | DevOps Engineer | Ensuring zero critical vulnerabilities guarantees that only secure and low-risk software reaches production. No Critical Risks + Secure Release + High Confidence
29 | Ensure no hardcoded secrets | DevOps Engineer | Ensuring no hardcoded secrets protects the system from credential leaks and significantly reduces security risk. No Secret Exposure + Strong Security + Safe Codebase
30 | Validate compliance checks | DevOps Engineer | Validating compliance checks ensures every release meets required standards, reducing risk and enabling confident delivery. Compliance Assurance + Reduced Risk + Built-in Governance
Metrics
| Thrive | Scrum Master | Thrive transforms engineering into a data-driven, high-performing system that delivers faster, safer, and more customer-focused outcomes. Faster Delivery + Better Quality + Higher Productivity + Stronger Customer Focus

## 3. Continuous Deployment
# | Task/Activity | Responsible Role | Outcome | Toolkit
Deployment Flow
1 | Setup Infrastructure as Code (IaC) | DevOps Engineer | Infrastructure as Code enables fast, consistent, and reliable environment setup, making infrastructure scalable and fully controlled. Automated + Consistent + Scalable Infrastructure
2 | Configure Dev environment | DevOps Engineer | Well-configured environments ensure smooth flow from development to release, enabling fast feedback, strong validation, and confident deployments. Faster Development + Assured Quality + Safe & Predictable Releases
3 | Configure QA environment | DevOps Engineer
4 | Configure Staging environment | DevOps Engineer
5 | Configure Production environment | DevOps Engineer
6 | Implement automated promotion pipeline | DevOps Engineer | An automated promotion pipeline ensures only validated, high-quality builds move seamlessly from development to production. Controlled Promotion + Built-in Quality + Faster & Safer Releases
Advanced Validation (Non-Functional Testing)
7 | Execute performance testing | Performance Engineer | Performance testing ensures the system can handle real-world load reliably, delivering consistent and scalable user experience. Validated Performance + Scalability Confidence + Production Stability
8 | Execute load testing | Performance Engineer | Load testing ensures the system can handle expected user demand reliably without performance degradation. Validated Real-World Performance + Stability + Capacity Confidence
9 | Execute stress testing | Performance Engineer | Stress testing reveals how the system behaves beyond its limits, enabling teams to build resilient and failure-tolerant architectures. Known System Limits + Controlled Failure Behavior + Improved Resilience
| Compliance | Developer | it is ensuring the system, processes, and software consistently meet required legal, regulatory, security, and organizational standards throughout its lifecycle. Regulatory Assurance + Reduced Risk + Trusted & Governed Systems
10 | Execute DAST (Dynamic Application Security Testing) | Security Engineer | The outcome of executing DAST (Dynamic Application Security Testing) is not just a scan result—it’s validation of application security from an external attacker’s perspective while the system is running. Runtime Vulnerability Detection + Real Attack Simulation + Stronger Security
11 | Validate scalability | Performance Engineer | The outcome of validating scalability is not just a test result—it is confidence that the system can grow with increasing load while maintaining performance, stability, and efficiency. Proven Scalability + Stable Performance + Growth Confidence
12 | Test disaster recovery | DevOps Engineer | The outcome of testing disaster recovery (DR) is not just a successful drill—it is confidence that the system can recover quickly, safely, and completely after a major failure or outage. Proven Recovery + Controlled Data Loss + Business Continuity Assurance
Verification Before Release
13 | Setup monitoring (Prometheus Grafana) | DevOps Engineer | The outcome of setting up monitoring using Prometheus and Grafana is not just dashboards—it is real-time visibility, proactive detection, and data-driven operational control over system health and performance. Real-Time Visibility + Faster Detection + Proactive Operations
14 | Configure logging. Validate deployment health via logs (ELK Stack Grafana) | DevOps Engineer | The outcome of configuring logging and validating deployment health using logs (e.g., Elasticsearch, Logstash, Kibana / Grafana) is not just log collection—it is complete visibility into system behavior with the ability to detect, diagnose, and validate deployment health in real time. Centralized Logs + Deployment Validation + Faster Debugging + Full Visibility
15 | Implement tracing Telemetrics (Jaeger) | DevOps Engineer | The outcome of implementing tracing (telemetry) using Jaeger is not just tracking requests—it is end-to-end visibility of how requests flow through distributed systems, enabling fast diagnosis of performance and failure issues. End-to-End Visibility + Faster Debugging + Performance Optimization
17 | Review metrics and alerts | DevOps Engineer | The outcome of reviewing metrics and alerts is not just looking at dashboards—it is turning operational data into actionable insights that improve system reliability, performance, and business outcomes. Early Detection + Faster Response + Data-Driven Optimization
18 | Verify system readiness | Release Manager | The outcome of verifying system readiness is not just a checklist completion—it is confidence that the system is fully prepared, stable, secure, and capable of handling production workloads before release. Production-Ready + Risk-Free + Fully Validated System
Metrics
| Thrive | Scrum Master | Thrive transforms engineering into a data-driven, high-performing system that delivers faster, safer, and more customer-focused outcomes. Faster Delivery + Better Quality + Higher Productivity + Stronger Customer Focus

## 4. Release on Demand
# | Task/Activity | Responsible Role | Outcome | Toolkits
Strategic Release
1 | Decouple deployment from release | Release Manager | Decoupling deployment from release enables faster delivery while giving the business full control over when features reach users. Controlled Releases + Reduced Risk + Faster Delivery + Better Experimentation
2 | Implement feature toggles | Tech Lead | The outcome of implementing feature toggles (feature flags) is not just conditional code—it’s real-time control over feature exposure, enabling safer releases, experimentation, and faster delivery. Controlled Release + Reduced Risk + Faster Delivery + Experimentation
3 | Setup A/B testing framework | Product Manager | The outcome of setting up an A/B testing framework is not just running experiments—it’s enabling data-driven decisions by validating which product changes actually improve user behavior and business outcomes. Experimentation + Data-Driven Decisions + Improved Customer & Business Outcomes
4 | Plan phased rollout strategy | Release Manager | The outcome of planning a phased rollout strategy is not just a rollout plan—it’s a controlled, low-risk way to introduce changes while continuously validating impact and maintaining system stability. Controlled Rollout + Reduced Risk + Faster Feedback + Confident Releases
5 | Configure canary deployments | DevOps Engineer | Canary deployments enable safe, incremental releases by validating changes with real users before full rollout. Safe Release + Early Detection + Data-Driven Rollout + Fast Recovery
6 | Establish rollback procedures | DevOps Engineer | Rollback procedures ensure that any failure can be quickly reversed, minimizing impact and enabling safe, continuous delivery. Fast Recovery + Reduced Risk + Confident Releases
Stability and Enduring Value
7 | Define SLAs/SLOs | Service Manager | Defining SLAs and SLOs establishes clear reliability commitments, aligning business expectations with engineering performance. Measurable Reliability + Business Alignment + Data-Driven Operations
8 | Monitor SLA compliance | DevOps Engineer | Monitoring SLA compliance ensures service commitments are consistently met, enabling proactive action and maintaining customer trust. SLA Assurance + Early Detection + Faster Response + Continuous Improvement
9 | Implement incident management | Service Manager | The outcome of implementing incident management is not just handling outages—it’s a structured, repeatable way to detect, respond to, resolve, and learn from incidents to minimize impact and improve system reliability over time. Faster Resolution + Reduced Impact + Continuous Improvement
10 | Execute continuous patching | DevOps Engineer | Continuous patching ensures systems remain secure, stable, and up to date by proactively addressing vulnerabilities with minimal disruption. Continuous Security + Stability + Compliance + Reduced Risk
11 | Conduct post-release reviews | Release Manager | The outcome of conducting post-release reviews is not just a retrospective—it’s turning every release into a learning opportunity that improves future delivery, quality, and reliability. Learning + Improvement + Better Quality + Stronger Processes
12 | Maintain system stability | DevOps Team | The outcome of maintaining system stability is not just keeping the system running—it’s ensuring consistent, reliable, and predictable system behavior under all operating conditions. Reliable Operation + High Availability + Consistent Performance
Closing the Loop - Feedback to CE
13 | Collect user engagement metrics | Product Manager | The outcome of collecting user engagement metrics is not just gathering data—it’s understanding how users actually interact with your product, enabling informed decisions that improve experience and business outcomes. User Insights + Better Decisions + Improved Experience + Business Growth
14 | Track conversion rates | Product Manager | The outcome of tracking conversion rates is not just measuring percentages—it’s understanding how effectively your product turns user actions into meaningful business outcomes. Measurable Business Impact + Funnel Insights + Improved Conversion + Revenue Growth
16 | Analyze real usage data | Data Analyst | Analyzing real usage data turns customer behavior into actionable insights, enabling continuous product and business improvement. Real User Insights + Better Decisions + Improved Experience + Business Growth
17 | Generate insights and improvements | Product Owner | The outcome of generating insights and improvements is not just analysis—it’s turning data into concrete actions that enhance product value, user experience, and business performance. Actionable Insights + Continuous Improvement + Better Experience + Business Growth